## POAM
Finding ID | Risk ID | Finding Description | Remediation Action | Owner | Priority | Target Date | Status
F-01 | R-01 | No authentication implemented | Implement authentication system (JWT / session-based login) | Developer | High | Pending management approval | Open
F-02 | R-02 | No role-based access control (RBAC) implemented | Implement RBAC middleware to enforce role-based authorization (Admin, User, etc.) | Developer | High | Pending management approval | Open
F-03 | R-02 | Excessive privileged access granted to developer | Apply least privilege principle and restrict access to critical systems (DB, deployment, secrets) | System Owner | High | Pending management approval | Open
F-04 | R-03 | Partial encryption of PII data | Implement full encryption for all sensitive data fields (name, address, contact details) | Developer | High | Pending management approval | Open
F-05 | R-04 | Sensitive credentials stored in environment file without access control | Implement secure secrets management solution (e.g., environment access restriction or secret manager) | Developer | High | Pending management approval | Open
F-06 | R-05 | Direct commits to production without review | Implement pull request workflow with mandatory approval before merging | Developer | High | Pending management approval | Open
F-07 | R-06 | Lack of user activity and audit logging | Implement centralized logging system capturing user actions and security events | Developer | High | Pending management approval | Open
F-08 | R-06 | No alerting or monitoring mechanism | Implement monitoring and alerting system for suspicious activities (e.g., failed logins, abnormal behavior) | Developer | Medium | Pending management approval | Open
F-09 | R-07 | No third-party risk assessment performed | Establish vendor risk assessment process for third-party services (Stripe, hosting, etc.) | System Owner | Medium | Pending management approval | Open
F-10 | R-02 | No periodic access review proces | Implement periodic user access review (UAR) process | System Owner | Medium | Pending management approval | Open
F-11 | R-06 | No incident response plan defined | Develop and document incident response procedures | System Owner | High | Pending management approval | Open
F-12 | R-06 | No backup and recovery mechanism | Implement automated backup and recovery solution | Developer | High | Pending management approval | Open
F-13 | R-04 | No secure configuration baseline | Define and implement secure configuration standards | Developer | Medium | Pending management approval | Open
F-14 | R-03 | Inconsistent input validation | Implement strict input validation and sanitization across all endpoints | Developer | High | Pending management approval | Open
F-15 | R-03 | No data retention policy | Define and enforce data retention and deletion policies | System Owner | Medium | Pending management approval | Open
F-16 | R-02 | No access approval workflow | Implement formal access request and approval process | System Owner | Medium | Pending management approval | Open
F-17 | R-04 | No security awareness training | Implement security awareness training program | System Owner | Low | Pending management approval | Open
F-18 | R-04 | No formal policies or governance framework | Develop and document security policies and procedures | System Owner | Medium | Pending management approval | Open